## Instructions
Instructions for making a Procurement Plan | See Ch.4 in the Procurement Manual for additional guidance.
The Procurement Plan shall answer the questions of what to buy, when to buy, estimated prices and how to buy.
A Procurement Plan shall be drafted as a part of the project application. This is to ensure that all procurement and logistic costs are included in the budget and that procurement time constraints are considered in the activity plan. It is the responsibility of the Procurement Committee to ensure that the Procurement Plan is prepared and followed.
The Procurement Plan is a dynamic planning tool which will change during the project period. Make sure to document the process and the development of the Procurement Plan by saving a version of each updated excel sheet.
The procurement plan should be developed jointly by programme and logistics, ideally with the assistance of a finance colleague. In cooperation with relevant project staff, it shall be established which resources are required to be procured (supplies, services, works). At the stage of preparing a procurement plan, it is important to determine the minimum technical specifications. Moreover considerations regarding the use of e.g. community involved procurement, Framework Contracts, vouchers etc. shall be integrated in the procurement plan.
1) Group resources into lots
What is a lot?
Preparing of lots Preparing lots is the process of grouping resources which can be purchased from one contractor in order to obtain the best quality and prices for the required resources for a project. In other contexts the same resources may have to be purchased separately as the suppliers in the market have more specific product groups and will not be able to deliver various resources.
The preparing of lots is foremost defined by the market structure. There is no fixed solution to what a lot includes, thus it is important to obtain market knowledge via the market survey.
In some contexts, it is possible to group many different resources into one lot and purchase from one contractor, as this is how the market is structured.
To do this exercise, it is recommended that you paste the budget into the "budget" tab in this document for easy reference. You can do the same with the activity plan/narrative budget.
Example: Most markets are structured in a way that does not allow us to purchase motorcycles and computers from the same supplier.
Thus there would be two lots - one for the computers and one for the motorcycles. However, in Cambodia a Procurement Officer found
that he could purchase both the computers and the motorcycles from the same supplier, and thus in this contexts it was one lot.
2) Define procurement procedures
In the supporting info tab in this document you will find the manual thresholds. If your office have different thresholds, paste yours in for easy reference.
Review the timeline for each procedure (in the supporting info tab) and add time for delivery depending on local suppliers. Combined, this will give you a start date for when to initiate the procurement processes.
3) Request for derogation(s) - if needed (this should be done as part of the donor project funding application)
4) Post the Advertisement of Business Opportunities
Once you know what you will be procuring for this specific project, post an advertisement of business opportunities. See Proc. Manual for more info.

## SUPPLY
ANNEX GEN 7-1: Template for Procurement Plan
PROCUREMENT PLAN
Project title: |  |  | <Insert>
Project PID: |  |  | <Insert>
Donor: |  |  | <Insert>
Project timeframe: |  |  | <Insert>
Preparation date: |  |  | <Insert>
Revision date & version no. |  |  | <Insert>
Derogations: |  |  | <Insert>
Procurement Plan for Supply, Service and Works
Budget line number | Description of lots and items | Quantity | Note Number | Estimated cost including VAT and taxes EUR | Procurement procedure | Date needed at project site + start date
[6 empty] | A | B | C | D | E
[8 empty] | (A+B) |  | (D-C)
[6 empty] | Time to carry out the procurement procedure (incl time for import/export permits and registration) | Delivery time by the supplier + transit time + custom clearance + local haulage | Total delivery time | Goods required by | Procure-ment start date
(Note: remember to adjust activity plan)
[6 empty] | Days | Days | Days | Date | Date
SUPPLY
Total value lot XX
Total value lot XX
TOTAL PROCUREMENT PLAN SUPPLY CONTRACTS VALUE
Note 1: <Insert information>
Note 2: <Insert information>

## SERVICES
ANNEX GEN 7-1: Template for Procurement Plan
PROCUREMENT PLAN
Project title: |  |  | <Insert>
Project PID: |  |  | <Insert>
Donor: |  |  | <Insert>
Project timeframe: |  |  | <Insert>
Preparation date: |  |  | <Insert>
Revision date & version no. |  |  | <Insert>
Derogations: |  |  | <Insert>
Procurement Plan for Supply, Service and Works
Budget line number | Description of lots and items | Quantity | Note Number | Estimated cost including VAT and taxes EUR | Procurement procedure | Date needed at project site + start date
[6 empty] | A | B | C | D | E
[8 empty] | (A+B) |  | (D-C)
[6 empty] | Time to carry out the procurement procedure (incl time for import/export permits and registration) | Delivery time by the supplier + transit time + custom clearance + local haulage | Total delivery time | Goods required by | Procure-ment start date
(Note: remember to adjust activity plan)
[6 empty] | Days | Days | Days | Date | Date
SERVICES
Total value lot XX
Total value lot XX
TOTAL PROCUREMENT PLAN SERVICE CONTRACTS VALUE
Note 1: <Insert information>
Note 2: <Insert information>

## WORKS
ANNEX GEN 7-1: Template for Procurement Plan
PROCUREMENT PLAN
Project title: |  |  | <Insert>
Project PID: |  |  | <Insert>
Donor: |  |  | <Insert>
Project timeframe: |  |  | <Insert>
Preparation date: |  |  | <Insert>
Revision date & version no. |  |  | <Insert>
Derogations: |  |  | <Insert>
Procurement Plan for Supply, Service and Works
Budget line number | Description of lots and items | Quantity | Note Number | Estimated cost including VAT and taxes EUR | Procurement procedure | Date needed at project site + start date
[6 empty] | A | B | C | D | E
[8 empty] | (A+B) |  | (D-C)
[6 empty] | Time to carry out the procurement procedure (incl time for import/export permits and registration) | Delivery time by the supplier + transit time + custom clearance + local haulage | Total delivery time | Goods required by | Procure-ment start date
(Note: remember to adjust activity plan)
[6 empty] | Days | Days | Days | Date | Date
WORKS
Total value lot XX
Total value lot XX
TOTAL PROCUREMENT PLAN SERVICE CONTRACTS VALUE
Note 1: <Insert information>
Note 2: <Insert information>

## Consolidated
ANNEX GEN 7-1: Template for Procurement Plan
PROCUREMENT PLAN
Project title: |  |  | <Insert> | [11 empty] | <Insert Logo>
Project PID: |  |  | <Insert>
Donor: |  |  | <Insert>
Project timeframe: |  |  | <Insert>
Preparation date: |  |  | <Insert>
Revision date & version no. |  |  | <Insert>
Derogations: |  |  | <Insert>
Procurement Plan for Supply, Service and Works | [10 empty] | This section can be deleted if Procurement Tracker is updated
Budget line number | Description of lots and items | Quantity | Note Number | Estimated cost including VAT and taxes EUR | Procurement procedure | Date needed at project site + start date |  |  |  |  | Actual Procurement
[6 empty] | A | B | C | D | E | PR File Reference in procurment tracker | Actual procurement procedure | Contractor selected | Actual Quantity | Contract value incl. VAT and taxes | Contract value incl. VAT and taxes | Voucher/ Transaction no.
[8 empty] | (A+B) |  | (D-C)
[6 empty] | Time to carry out the procurement procedure (incl time for import/export permits and registration) | Delivery time by the supplier + transit time + custom clearance + local haulage | Total delivery time | Goods required by | Procure-ment start date
[10 empty] | (Note: remember to adjust activity plan) |  |  |  |  | <Insert local currency> | EUR
[6 empty] | Days | Days | Days | Date | Date
Copy and paste here from other tabs (Supply, Services and Works) when completed
TOTAL PROCUREMENT PLAN VALUE
Note 1: <Insert information>
Note 2: <Insert information>
Procurement Plan approved by:
Name |  |  |  | Position
Signature |  |  |  | Date

## Budget
Please insert budget here for easy reference

## Supporting Info
Manual Thresholds (replace with local ones when relevant) |  | Timelines for procurement
The following schedules are based on estimates of the time needed to carry out each procurement procedure.
Supply |  | Time schedule for a Negotiated Procedure
Up to EUR 9,999 | Simple Procedure | Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
EUR 10,000-149,999 | Negotitated Procedure | Advertisement of Business Opportunities
EUR 150,000-299,999 | Local Open Tender Procedure
Above EUR 300,000 | International Open Tender Procedure | Prepare technical specifications/TOR and RFQ/RFP
Services
Up to EUR 9,999 | Simple Procedure
EUR 10,000-149,999 | Negotitated Procedure | RFQ/RFP bid flow. It is recommended that suppliers/candidates have at least 14-30 days to submit their quote
EUR 150,000-299,999 | Local Open Tender Procedure | Evaluation of quotes
Above EUR 300,000 | International Open Tender Procedure | Contract negotiations and award
Works |  | Delivery delay | [5 empty] | Depending on commodity
Up to EUR 9,999 | Simple Procedure | Customs clearance | [5 empty] | Depending on country
EUR 10,000-299,999 | Negotitated Procedure | Supplier’s delivery time to site
300,000-2,999,999 | Local Open Tender Procedure
Above 3,000,000 | International Open Tender Procedure | Time schedule for a Local Open Tender
|  | Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Note:If a Donor's thresholds are stricter than those of NCA, we follow the donor's thresholds. |  | Prepare technical specifications and tender documents
Advertisement of Tender Notice
Tender bid flow. It is recommended that suppliers/candidates have a minimum of 21 days to submit their tender
Tender evaluation, clarifications
Contract negotiations and award
Contract signing
|  | Delivery delay | [10 empty] | Depending on commodity
|  | Customs clearance | [10 empty] | Depending on country
Supplier’s delivery time to site
Time schedule for an International Open Tender
|  | Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Prepare technical specifications and tender documents
Advertisement of Tender Notice
Tender bid flow. It is recommended that suppliers/candidates have a minimum of 30 days to submit their tender
Tender evaluation, clarifications
Contract negotiations and award
Contract signing
|  | Delivery delay | [12 empty] | Depending on commodity
|  | Customs clearance | [12 empty] | Depending on country
Supplier’s delivery time to site
Procurement Thresholds
If a partners procurment threshold is strickter than NCA's, partner is expected to use them in all procurements. If there are special requirments from the back donor, that will always be adhered to wheather using NCA's or own procurment procedures.