## SUPPLY
PROCUREMENT PLAN
Project title: |  |  | NCA WASH Project
Project PID: |  |  | 999999
Donor: |  |  | International Funding Agency
Project timeframe: |  |  | 01 January 20XX to 31 December 20XX
Preparation date: |  |  | 15 December 20XX
Revision date & version no. |  |  | v1
Derogations: |  |  | See notes
Procurement Plan for Supply, Service and Works
Budget line number | Description of lots and items | Quantity | Note Number | Estimated cost including VAT and taxes EUR | Procurement procedure | Date needed at project site + start date
[6 empty] | A | B | C | D | E
[8 empty] | (A+B) |  | (D-C)
[6 empty] | Time to carry out the procurement procedure (incl time for import/export permits and registration) | Delivery time by the supplier + transit time + custom clearance + local haulage | Total delivery time | Goods required by | Procure-ment start date
(Note: remember to adjust activity plan)
[6 empty] | Days | Days | Days | Date | Date
SUPPLY
2.2 | DelAgua Kit Site 1 | 2 |  | 4400
2.3 | Consumables for water treatment and monitoring 3 month | 1 |  | 1800
2.9 | DelAgua Kit Site 2 | 2 |  | 4400
2.10 | Consumables for water treatment and monitoring 6 month | 1 |  | 3600
| Total value lot 1 |  | 1 | 14200 | Simple | 7 | 28 | 35 | 01 May xx | 26 Mar xx
2.6 | 15,000 ltr tank | 8 |  | 24000
2.12 | Jerry cans | 4320 |  | 73309
| Total value lot 2 |  |  | 97309 | Negotiated | 28 | 14 | 42 | 30 Jun xx | 19 Apr xx
2.15 | Latrine materials Site 1 | 28 |  | 6958
2.16 | Shower materials Site 1 | 28 |  | 8230
2.21 | Latrine materials Site 2 | 192 |  | 47709
2.22 | Shower materials Site 2 | 192 |  | 56436
| Total value lot 3 |  | 2 | 119333 | Negotiated | 28 | 14 | 42 | 01 May xx | 18 Mar xx
2.13 | Evaluation, supply & installation of solar pumping system | 12 |  | 363636
| Total value lot 4 |  |  | 363636 | International Open | 42 | 60 | 142 | 30 Sep xx | 17 Jun xx
2.27 | Hygiene kits | 1080 |  | 51055
| Total value lot 5 |  |  | 51055 | Negotiated | 28 | 14 | 42 | 01 May xx | 18 Mar xx
4.1 | Computers | 8 |  | 16970
4.2 | Printers | 2 |  | 3030
| Total value lot 6 |  |  | 20000 | Negotiated | 42 | 7 | 49 | 14 Apr xx | 06 Mar xx
4.3 | Office supplies | 12 |  | 7273
| Total value lot 7 |  |  | 7273 | Simple | 5 | 5 | 10 | 15 Jan xx | 05 Jan xx
TOTAL PROCUREMENT PLAN SUPPLY CONTRACTS VALUE |  |  |  | 672806
Note 1: Derogation to procure kits and consumables from sole supplier due to compatibility and training
Note 2: All items to be procured in bulk and stored in warehouse

## SERVICES
PROCUREMENT PLAN
Project title: |  |  | NCA WASH Project
Project PID: |  |  | 999999
Donor: |  |  | International Funding Agency
Project timeframe: |  |  | 01 January 20XX to 31 December 20XX
Preparation date: |  |  | 15 December 20XX
Revision date & version no. |  |  | v1
Derogations: |  |  | See notes
Procurement Plan for Supply, Service and Works
Budget line number | Description of lots and items | Quantity | Note Number | Estimated cost including VAT and taxes EUR | Procurement procedure | Date needed at project site + start date
[6 empty] | A | B | C | D | E
[8 empty] | (A+B) |  | (D-C)
[6 empty] | Time to carry out the procurement procedure (incl time for import/export permits and registration) | Delivery time by the supplier + transit time + custom clearance + local haulage | Total delivery time | Goods required by | Procure-ment start date
(Note: remember to adjust activity plan)
[6 empty] | Days | Days | Days | Date | Date
SERVICES
2.1 | Water trucking in Site 1 | 1 |  | 65455
2.5 | Water trucking in Site 2 | 1 |  | 174545
| Lot 8 Sub lot A subtotal |  |  | 240000
2.20 | Desludging and toilet maintenance Site 1 | 1 |  | 21818
2.26 | Desludging and toilet maintenance Site 2 | 1 |  | 21818
| Lot 8 Sub lot B subtotal |  |  | 43636
| Total value lot 8 |  | 3 | 283636 | Local Open | 42 | on going | 42 | 28 Feb xx | 17 Jan xx
3.2 | Accommodation | 6 |  | 7273
| Total value lot 9 |  |  | 7273 | Simple | 5 | 5 | 10 | 10 Jan xx | 01 Jan xx
3.4 | Monitoring and Evaluation Consultant | 1 |  | 2500
| Total value Lot 10 |  |  | 2500 | Simple | 28 | 7 | 35 | 31 Dec xx | 26 Nov xx
3.1 | Domestic Air Tickets | 5 |  | 2273
| Total value lot 11 |  |  | 2273 | Simple | 7 | 0 | 7 | 01 Feb xx | 24 Jan xx
5.3 | Communication (telephone, internet) | 12 |  | 8727
| Total value lot 12 |  | 4 | 8727 | Simple | 28 | 7 | 35 | 15 Feb xx | 11 Jan xx
5.4 | Security for office and warehouse | 12 |  | 17455
| Total value lot 13 |  |  | 17455 | Negotiated | 28 | 7 | 35 | 15 Feb xx | 11 Jan xx
TOTAL PROCUREMENT PLAN SERVICE CONTRACTS VALUE |  |  |  | 321864
Note 3: Framework contracts
Note 4: Service provider must provide both mobile telephone and internet services

## WORKS
PROCUREMENT PLAN
Project title: |  |  | NCA WASH Project
Project PID: |  |  | 999999
Donor: |  |  | International Funding Agency
Project timeframe: |  |  | 01 January 20XX to 31 December 20XX
Preparation date: |  |  | 15 December 20XX
Revision date & version no. |  |  | v1
Derogations: |  |  | See notes
Procurement Plan for Supply, Service and Works
Budget line number | Description of lots and items | Quantity | Note Number | Estimated cost including VAT and taxes EUR | Procurement procedure | Date needed at project site + start date
[6 empty] | A | B | C | D | E
[8 empty] | (A+B) |  | (D-C)
[6 empty] | Time to carry out the procurement procedure (incl time for import/export permits and registration) | Delivery time by the supplier + transit time + custom clearance + local haulage | Total delivery time | Goods required by | Procure-ment start date
(Note: remember to adjust activity plan)
[6 empty] | Days | Days | Days | Date | Date
WORKS
2.7 | Construction on tap stands | 8 |  | 4606
| Total value lot 14 |  |  | 4606 | Simple | 14 | 14 | 28 | 30 Jun xx | 02 Jun xx
2.8 | Distribution system instlallation | 2 |  | 1394
| Total value lot 15 |  |  | 1394 | Simple | 14 | 14 | 28 | 30 Jun xx | 02 Jun xx
2.14 | Extend distribution network | 1 |  | 200000
| Total value lot 16 |  | 5 | 200000 | Negotiated | 35 | 60 | 95 | 01 Jun xx | 25 Feb xx
TOTAL PROCUREMENT PLAN WORKS CONTRACTS VALUE |  |  |  | 206000
Note 5: Refer to site plans and Bill of Quantities for details

## Consolidated
PROCUREMENT PLAN
Project title: |  |  |  | NCA WASH Project
Project PID: |  |  |  | 999999
Donor: |  |  |  | International Funding Agency
Project timeframe: |  |  |  | 01 January 20XX to 31 December 20XX
Preparation date: |  |  |  | 15 December 20XX
Revision date & version no. |  |  |  | v1
Derogations: |  |  |  | See notes
Procurement Plan for Supply, Service and Works | [11 empty] | This section can be deleted if Procurement Tracker is updated
Budget line number | Lot Number | Description of lots and items | Quantity | Note Number | Estimated cost including VAT and taxes EUR | Procurement procedure | Date needed at project site + start date |  |  |  |  | Actual Procurement
[7 empty] | A | B | C | D | E | PR File Reference in procurment tracker | Actual procurement procedure | Contractor selected | Actual Quantity | Contract value incl. VAT and taxes | Contract value incl. VAT and taxes | Voucher/ Transaction no.
[9 empty] | (A+B) |  | (D-C)
[7 empty] | Time to carry out the procurement procedure (incl time for import/export permits and registration) | Delivery time by the supplier + transit time + custom clearance + local haulage | Total delivery time | Goods required by | Procure-ment start date
[11 empty] | (Note: remember to adjust activity plan) |  |  |  |  | <Insert local currency> | EUR
[7 empty] | Days | Days | Days | Date | Date
SUPPLY
2.2 | Lot 1 | DelAgua Kit Site 1 | 2 |  | 4400
2.3 |  | Consumables for water treatment and monitoring 3 month | 1 |  | 1800
2.9 |  | DelAgua Kit Site 2 | 2 |  | 4400
2.10 |  | Consumables for water treatment and monitoring 6 month | 1 |  | 3600
|  | Total value lot 1 |  | 1 | 14200 | Simple | 7 | 28 | 35 | 01 May xx | 26 Mar xx
2.6 | Lot 2 | 15,000 ltr tank | 8 |  | 24000
2.12 |  | Jerry cans | 4320 |  | 73309
|  | Total value lot 2 |  | 2 | 97309 | Negotiated | 28 | 14 | 42 | 30 Jun xx | 19 Apr xx
2.15 | Lot 3 | Latrine materials Site 1 | 28 |  | 6958
2.16 |  | Shower materials Site 1 | 28 |  | 8230
2.21 |  | Latrine materials Site 2 | 192 |  | 47709
2.22 |  | Shower materials Site 2 | 192 |  | 56436
|  | Total value lot 3 |  |  | 119333 | Negotiated | 28 | 14 | 42 | 01 May xx | 18 Mar xx
2.13 | Lot 4 | Evaluation, supply & installation of solar pumping system | 12 |  | 363636
|  | Total value Lot 4 |  |  | 363636 | International open | 42 | 60 | 142 | 30 Sep xx | 17 Jun xx
2.27 | Lot 5 | Hygiene kits | 1080 |  | 51055
|  | Total value lot 5 |  |  | 51055 | Negotiated | 28 | 14 | 42 | 01 May xx | 18 Mar xx
4.1 | Lot 6 | Computers | 8 |  | 16970
4.2 |  | Printers | 2 |  | 3030
|  | Total value lot 6 |  |  | 20000 | Negotiated | 42 | 7 | 49 | 14 Apr xx | 06 Mar xx
4.3 | Lot 7 | Office supplies | 12 |  | 7273
|  | Total value lot 7 |  |  | 7273 | Simple | 5 | 5 | 10 | 15 Jan xx | 05 Jan xx
TOTAL PROCUREMENT PLAN SUPPLY CONTRACTS VALUE |  |  |  |  | 672806
SERVICES
2.1 | Lot 8 Sub lot A | Water trucking in Site 1 | 1 |  | 65455
2.5 |  | Water trucking in Site 2 | 1 |  | 174545
|  | Lot 8 Sub lot A subtotal |  |  | 240000
2.20 | Lot 8 Sub lot B | Desludging and toilet maintenance Site 1 | 1 |  | 21818
2.26 |  | Desludging and toilet maintenance Site 2 | 1 |  | 21818
|  | Lot 8 Sub lot B subtotal |  | 3 | 43636
|  | Total value lot 8 |  |  | 283636 | Local Open | 42 | on going | 42 | 28 Feb xx | 17 Jan xx
3.2 | Lot 9 | Accommodation | 6 |  | 7273
|  | Total value lot 9 |  |  | 7273 | Simple | 5 | 5 | 10 | 10 Jan xx | 01 Jan xx
3.4 | Lot 10 | Monitoring and Evaluation Consultant | 1 |  | 2500
|  | Total value Lot 10 |  |  | 2500 | Simple | 28 | 7 | 35 | 31 Dec xx | 26 Nov xx
3.1 | Lot 11 | Domestic Air Tickets | 5 |  | 2273
|  | Total value lot 11 |  |  | 2273 | Simple | 7 | 0 | 7 | 01 Feb xx | 24 Jan xx
5.3 | Lot 12 | Communication (telephone, internet) | 12 |  | 8727
|  | Total value lot 12 |  | 4 | 8727 | Simple | 28 | 7 | 35 | 15 Feb xx | 11 Jan xx
5.4 | Lot 13 | Security for office and warehouse | 12 |  | 17455
|  | Total value lot 13 |  |  | 17455 | Negotiated | 28 | 7 | 35 | 15 Feb xx | 11 Jan xx
TOTAL PROCUREMENT PLAN SERVICE CONTRACTS VALUE |  |  |  |  | 321864
WORKS
2.7 | Lot 14 | Construction on tap stands | 8 |  | 4606
|  | Total value lot 14 |  |  | 4606 | Simple | 14 | 14 | 28 | 30 Jun xx | 02 Jun xx
2.8 | Lot 15 | Distribution system instlallation | 2 |  | 1394
|  | Total value lot 15 |  |  | 1394 | Simple | 14 | 14 | 28 | 30 Jun xx | 02 Jun xx
2.14 | Lot 16 | Extend distribution network | 1 |  | 200000
|  | Total value lot 16 |  | 5 | 200000 | Negotiated | 35 | 60 | 95 | 01 Jun xx | 25 Feb xx
TOTAL PROCUREMENT PLAN WORKS CONTRACTS VALUE |  |  |  |  | 206000
TOTAL PROCUREMENT PLAN VALUE |  |  |  |  | 1200670
Note 1: Derogation to procure kits and consumables from sole supplier due to compatibility and training
Note 2: All items to be procured in bulk and stored in warehouse
Note 3: Framework contracts
Note 4: Service provider must provide both mobile telephone and internet services
Note 5: Refer to site plans and Bill of Quantities for details
Procurement Plan approved by:
Name |  |  |  | Position
Signature |  |  |  | Date

## Budget
NCA WASH PROJECT
| Activities / Item | Quantity | Unit | Unit cost Local currency | Total cost Local currency | Total cost EURO
1 | Personnel
1.1 | WASH Program Manager (1) | 12 | month | 813450 | 9761400 | 59160
1.2 | Water supply supervisor (1) | 12 | month | 683100 | 8197200 | 49680
1.3 | Sanitation and hygiene supervisor (1) | 12 | month | 683100 | 8197200 | 49680
1.4 | Logistics and procurement officer (1) | 12 | month | 440550 | 5286600 | 32040
1.5 | Driver (1) | 12 | month | 257400 | 3088800 | 18720
1.6 | Finance Officer | 12 | month | 440550 | 5286600 | 32040
1.7 | NCA Head Office WASH in Emergencies Specialist | 6 | month | 1320000 | 7920000 | 48000
| Subtotal Personnel |  |  |  | 47737800 | 289320
2 | Outcome 1a: water in Site 1 reception center
2.1 | Water trucking in Site 1 | 90 | days | 120000 | 10800000 | 65454.5455
water treatment and quality monitoring
2.2 | Delagua kit | 1 | unit | 363000 | 363000 | 2200
2.3 | consumables for water treatment and monitoring | 3 | month | 49500 | 148500 | 900
2.4 | water point supervisors refugee workers (10) | 900 | days | 1000 | 900000 | 5454.5455
Outcome 1b: water in Site 2 camp
2.5 | Water trucking in Site 2 | 180 | days | 160000 | 28800000 | 174545.4545
Installation of 4 storage capacity of 15,000 liters with distribution
2.6 | 15,000 liter tank | 8 | tank | 495000 | 3960000 | 24000
2.7 | construction of tap stands | 8 | unit cost | 95000 | 760000 | 4606.0606
2.8 | distribution system installation | 2 | unit cost | 115000 | 230000 | 1393.9394
water treatment and quality monitoring
2.9 | Delagua kit | 1 | unit | 363000 | 363000 | 2200
2.10 | consumables for water treatment and monitoring | 6 | month | 49500 | 297000 | 1800
2.11 | water point supervisors refugee workers (4) | 8 | supervisor | 180000 | 1440000 | 8727.2727
2.12 | distribution jerry cans (2 per family) | 4320 | unit | 2800 | 12096000 | 73309.0909
2.13 | Evaluation, supply and installation solar pumping system | 12 | lump sum | 5000000 | 60000000 | 363636.3636
2.14 | Extend the distribution network to the communal facilities (school, health centers, public space…) in the intervention area. | 1 | lump sum | 33000000 | 33000000 | 200000
| Subtotal Outcome 1 |  |  |  | 153157500 | 928227.2727
Outcome 2a: Sanitation Site 1 site
Latrines and showers Site 1
2.15 | latrine materials | 28 | materials per latrine | 41000 | 1148000 | 6957.5758
2.16 | shower materials | 28 | materials per shower | 48500 | 1358000 | 8230.303
2.17 | C4W supervisor of masons and construction workers (2) | 10 | days | 2000 | 20000 | 121.2121
2.18 | C4W latrine and shower construction workers (15) | 10 | days | 5000 | 50000 | 303.0303
2.19 | C4W latrine and shower cleaners (25) | 100 | month | 30000 | 3000000 | 18181.8182
2.20 | desludging trucks and toilet maintenance | 6 | months | 600000 | 3600000 | 21818.1818
Outcome 2b: Sanitation and Hygiene Site 2 site
Latrines and showers Site 2 12 villages
2.21 | latrine materials | 192 | materials per latrine | 41000 | 7872000 | 47709.0909
2.22 | shower materials | 192 | materials per shower | 48500 | 9312000 | 56436.3636
2.23 | C4W supervisor of masons and construction workers | 4 | month | 60000 | 240000 | 1454.5455
2.24 | C4W latrine and shower construction workers (15 workers) | 60 | days | 30000 | 1800000 | 10909.0909
2.25 | C4W latrine and shower cleaners (20) | 60 | days | 10000 | 600000 | 3636.3636
2.26 | desludging trucks and toilet maintenance | 6 | months | 600000 | 3600000 | 21818.1818
Hygiene in Site 2 camp
2.27 | hygiene kits for refugees | 1080 | kit | 7800 | 8424000 | 51054.5455
2.28 | replenishment hygiene kits | 1080 | kit | 6950 | 7506000 | 45490.9091
2.29 | hygiene promoters/community mobilizers (15) | 450 | days | 1000 | 450000 | 2727.2727
| Subtotal outcome 2 |  |  |  | 48980000 | 296848.4848
3. | Recruitment, Monitoring and Supervisory costs
3.1 | domestic air tickets | 5 | round trip ticket | 75000 | 375000 | 2272.7273
3.2 | accommodation | 6 | months | 200000 | 1200000 | 7272.7273
3.3 | per diem costs | 180 | days | 8250 | 1485000 | 9000
3.4 | Monitoring and Evaluation Consultant | 1 | LS | 412500 | 412500 | 2500
| Subtotal recruitment and monitoring costs |  |  |  | 3060000 | 18545.4545
4. | Supplies and Materials
4.1 | computers | 8 | laptop | 350000 | 2800000 | 16969.697
4.2 | printer | 2 | printer | 250000 | 500000 | 3030.303
4.3 | office supplies | 12 | month | 100000 | 1200000 | 7272.7273
| Subtotal |  |  |  | 4500000 | 27272.7273
5. | Admin Support costs
5.1 | office rental | 12 | month | 200000 | 2400000 | 14545.4545
5.2 | office utilities | 12 | month | 90000 | 1080000 | 6545.4545
5.3 | communication (telephone, internet) | 12 | month | 120000 | 1440000 | 8727.2727
5.4 | security for office and warehouse | 12 | month | 240000 | 2880000 | 17454.5455
5.5 | audit | 1 | fee | 660000 | 660000 | 4000
| Subtotal Admin support costs |  |  |  | 8460000 | 51272.7273
| Subtotal total project costs |  |  |  | 265895300 | 1611486.6667
6. | Head office 7% admin fee | 1 | LS |  | 18612671 | 112804.0667
| Total project costs |  |  |  | 284507971 | 1724290.7333